## Sheet1
Stage | Start Week | End Week | Estimated Hours | Milestone
Planning | 1 | 1 | 5 | Proposal Complete
Design | 1 | 2 | 10 | Design Mockups Complete
Development Sprint 1 | 2 | 4 | 15 | Core Features Built
Development Sprint 2 | 4 | 6 | 15 | Additional Features Added
Testing & Debugging | 6 | 7 | 10 | Testing Complete
Evaluation & Deployment | 8 | 8 | 5 | Project Submission